## Sheet1
FYP_Qinyuans_Project_implmentaion_Gantt_Chart
| Sem 1 | Week
Task no. | Task | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | -
1 | Ground work (Background research and learning ) | 0 | 0 | 0 | 0 | 0 | [10 empty] | END
2 | Interim Report | - | - | - | - | 0 | 0 | 0 | Dead Line Behind schdule!!!! | Behind schedule!!! | - | - | - | - | Exam | Exam | END
3 | Schematic Design | - | - | - | - | 0 | 0 | 0 | 0 | DONE | - | - | - | - | Exam | Exam | END
4 | Autumn Semester Presentation | - | - | - | - | 0 | 0 | 0 | 0 | Due to injry, I can's persent prototype (delayed), but it's well defined in the docments | - | - | - | - | Exam | Exam | END
5 | Code Development | - | - | - | - | - | - | - | - | 0 | 0 | 0 | 0 | 0 | Exam | Exam | END
6 | PCB Layout | - | - | - | - | - | - | - | - | - | - | - | 0 | 0 | Exam | Exam | END
| Winter Break | Week
Task no. | Task | - | 1 | 2 | 3 | 4 | 5 | END
1 | First PCB Schematic and Layout | - | Christmas | 0 | 0 | Order PCB |  | END
2 | PCB Testing | - |  | - | - | - | 0 | END
| Sem 2 | Week
Task no. | Task | - | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | - | - | - | - | - | -
1 | Final Report Due & Presentation | - | 0 | 0 | 0 | 0 | 0 | 0 | Final Report Due & Presentation |  | END
2 | PCB with STM32 on borad | - | 0 | Order PCB | - | - | - | - | - |  | END
3 | PCB Testing | - | - | - | 0 | 0 | System Verification | - | - |  | END